## Task
Assigned to | % Completed | Status | PPT Page # | Programing Group | Task | Task Description | Updated Comments | Comments
Crane | 0% | Open | 2 | Login/Authentication | Setup 4 user levels. | User Level's: 1.) Normal Operator (Viewing Only) 2.) Maintenance (Viewing and reset service counters and service alarms) Level 3. Maintenance (Calibration and Configuration of Adjustable Parameters) Level 4 Administrator (Viewing and Controlling)
Crane | 0% | Open | 2 | Login/Authentication | Auto logout if not active for 15 minutes | Auto logout if not active for 15 minutes
Crane | 0% | Open | 2 | Window title bar buttons | Add the correct logo | Add iOPS/JBT Logo
Paul/ED | 0% | Open | 2 | Layout | Add counts | Add count and critical alarms to header. ( Place holder in place need logic)
Crane | 0% | Open | 2 | Login/Authentication | Password rest | Need to a link to contact admin
Kevin | 0% | Open | 2 | Window title bar buttons | Disable the weather bug | Disable weather bug if no internet access. (if internet available enable )
Steve | 0% | Open | 2 | Graphics | Airport layout screen | Complete the AC graphics for multiple AC type
Crane/ED | 0% | Open | 3 | Screen Navigation | Add legend | Add the bridge legend to the gate screen
Kevin | 0% | Open | 3 | Layout | Change tittle airport | Change title and airport window tittle from Oman to Salalah
Paul | 0% | Open | 3 | Alarm HMI | Add fire alarm button to gate screen | Fire alarm button/alarm need to be added & flash when alarm is active
Paul | 0% | Open | 4 | Screen Navigation | Remove/Add single gate screen | Remove multiple gates and add the single gate screen.
Paul | 0% | Open | 4 | OPC Systems | OPC Tags | Configure OPC Systems/tags
Steve | 0% | Open | 5 | AC | AC Icon | Add gate Icon to the graphics
Kevin | 0% | Open | 4 | Screen Navigation | Add screens to left screen navigation bar | Add all screen to left screen nav. Airport Overview, Gate BH04-23F, Gate BH04-23B, Gate BH03-25F, Gate BH03-25B, Gate BH02-29F, Gate BH02-29B, Gate BH01-31F, Gate BH01-31B, Alarms, Server status, flight data and reports
Paul/Ed | 0% | Open | 5 | Service Counters | Add buttons | All buttons need to be added. Logic needed for button state/text changes based on current state
ED | 0% | Open | 5 | AC | AC Icon | Add a AC icon when gate is active
Steve | 0% | Open | 5 | Graphics | AC Docked Graphics | Develop gate graphics, AC and Jumbo AC graphics
Paul/ED | 0% | Open | 5 | Status HMI | Develop gate page | Develop gate page to include the alarm buttons
ED | 0% | Open | 5 | Status HMI | Jumbo AC docked button | Add jumbo AC button wen jumbo AC is docked
Kevin | 0% | Open | 5 | Service Counters | Service counter button | Add a service counter button to the screen. With link to service counter screen. Add service counter link to page and service counter tittle button both navigating to service counter page
Kevin | 0% | Open | 6 | Service Counters | Service counter button | Add a service counter button to the screen. With link to gate screen
Paul | 0% | Open | 5 | Service Counters | Remote enable/disable | Add the button to remote enable/disable
Paul | 0% | Open | 6 | Service Counters | Add service counter grid and resets | Develop services counter page and grid with resets
ED | 0% | Open | 6 | AC | AC Icon | Need to included AC icon wen gate is active
Paul | 0% | Open | 6 | Alarm HMI | Add remote enable and disable button | Add the tag for button remote enable and disable
Paul/John | 0% | Open | 7 | Alarm HMI | Add alarm page | Page for Alarms and Alarm Summary's: All alarms shall have alarm counters that are resettable for the operator. All Alarms shall be saved for a minimum of one year. Alarms shall be divided into separated groups. It Shall be possible to acknowledge an alarm in the alarm list and jump directly to the page containing the part triggering the alarm
Crane | 0% | Open | 8 | Server Status | Add server status page | SCADA Redundancy (Switch from one scada to the other from the HMI and to be able to see which one is active.
ED | 0% | Open | 9 |  | Add flight data screen | SCADA Shall Display (Aircraft Type and Model, Aircraft Position, Docking time, Undocking Time, Information from the 400hz Power Supply System Regarding Pits / Hatches, On Block and Off Block)
Crane/Paul | 0% | Open | 10 | Layout | Drop down menu | Develop a drop down menu to include Today, yesterday, last week, last month. Year to date
Crane/Paul | 0% | Open | 10 | Charts | Operations Charts | Create charts/graphs for gate utilization alarm by gate and current status filterable by drop down
Crane / Paul/ Ed | 0% | Open | 11 | Reports | Develop reports | Develop reports and filtering for reports
Willy | 0% | Open |  | PLC | PLC Configuration | Setup PLC
Paul | 0% | Open |  | OPC | OPC Systems | Configure OPC Systems/tags
Paul | 0% | Open |  | OPC | Kepware | Configure Kepware OPC server